## Sheet1
Task | Start Date | End Date | Duration (Days)
Define project scope and objectives | 2025-01-15 | 2025-01-20 | 5
Develop project charter | 2025-01-20 | 2025-01-23 | 3
Gather project requirements | 2025-01-23 | 2025-01-28 | 5
Assign roles and responsibilities | 2025-01-28 | 2025-01-30 | 2
Create initial project timeline | 2025-01-30 | 2025-02-01 | 2
Design homepage structure | 2025-02-01 | 2025-02-06 | 5
Create portfolio browsing interface | 2025-02-06 | 2025-02-10 | 4
Develop booking/payment system interface | 2025-02-10 | 2025-02-17 | 7
Conduct user testing on prototypes | 2025-02-17 | 2025-02-22 | 5
Set up code repository on GitHub | 2025-02-22 | 2025-02-23 | 1
Create homepage with portfolio display | 2025-02-23 | 2025-03-02 | 7
Implement booking calendar integration | 2025-03-02 | 2025-03-08 | 6
Develop responsive design features | 2025-03-08 | 2025-03-13 | 5
Implement secure payment gateway | 2025-03-13 | 2025-03-18 | 5
Handle booking/scheduling data storage | 2025-03-18 | 2025-03-23 | 5
Test booking process | 2025-03-23 | 2025-03-28 | 5
Verify payment gateway security | 2025-03-28 | 2025-03-31 | 3
Ensure desktop accessibility | 2025-03-31 | 2025-04-03 | 3
Resolve bugs and update code | 2025-04-03 | 2025-04-10 | 7
Deploy website to live hosting | 2025-04-10 | 2025-04-12 | 2
Monitor website performance | 2025-04-12 | 2025-04-17 | 5
Prepare final project presentation | 2025-04-17 | 2025-04-20 | 3