## Project Planner
Captura Development
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2025-01-06 to 2025-04-20
Project Initialization
| Define Scope and Objectives | 2025-01-06 | 5 | 1899-12-31 | 1900-01-03 | 25%
| Develop Project Charter | 1899-12-31 | 6 | 1899-12-31 | 1900-01-05 | 100%
| Gather Project Requirements | 2025-01-06 | 15 | 2025-01-06 |  | 35%
| Assign Roles and Responsibilities | 1900-01-03 | 8 | 1900-01-03 | 1900-01-05 | 10%
| Create Initial Project Timeline | 1900-01-03 | 2 | 1900-01-03 | 1900-01-07 | 85%
Website Design
Wireframe
| Design Homepage | 1900-01-04 | 1900-01-03 | 1900-01-04 | 1900-01-02 | 50%
| Portfolio Browsing | 1900-01-04 | 1900-01-01 | 1900-01-04 | 1900-01-04 | 60%
| Booking and Payment | 1900-01-04 | 1900-01-01 | 1900-01-04 | 1900-01-05 | 75%
| Implement Responsive Design Features | 1900-01-05 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 100%
| User Testing | 1900-01-05 | 1899-12-31 | 1900-01-04 | 1900-01-07 | 60%
Website Development
| Setup Code Repository on GitHub | 1900-01-08 | 2025-01-09 | 1900-01-08 | 2025-01-09 | 100%
Develop Frontend
| Create Homepage | 2025-01-30 | 10 |  |  | 0%
| Add portfolio to home page | 2025-01-30 | 10 |  |  | 0%
| Implement Booking Calendar Integration | 1900-01-08 | 4 | 1900-01-07 | 1900-01-04 | 1%
| Develop Responsive Design for Multiple Devices | 1900-01-09 | 5 | 1900-01-09 | 1900-01-02 | 80%
Develop Backend
| Implement Secure Payment Gateway | 1900-01-11 | 1900-01-05 | 1900-01-11 | 1900-01-06 | 0%
| Booking and Scheduling Data Storage | 1900-01-11 | 1899-12-31 | 1900-01-11 | 1900-01-04 | 0%
| Test Functionality | 1900-01-13 | 1900-01-04 | 1900-01-13 | 1900-01-05 | 0%
Testing and Quality Assurance
Functional Testing
| Test Booking Process | 1900-01-13 | 1900-01-07 | 1900-01-13 | 1900-01-01 | 44%
| Verify Payment Gateway Security | 1900-01-13 | 1900-01-06 | 1900-01-13 | 1900-01-02 | 0%
| Verify Photo Uploads to Expand Portfolio | 1900-01-14 | 1900-01-03 | 1900-01-14 | 1900-01-07 | 12%
Conduct Usability Testing
| Ensure Usability on Desktop, Tablet, and Mobile | 1900-01-14 | 1900-01-04 | 1900-01-14 | 1900-01-02 | 5%
| Collect Feedback for Improvements | 1900-01-14 | 1900-01-04 | 1900-01-14 | 1900-01-02 | 5%
| Implement Rating and Review System | 1900-01-15 | 1900-01-27 | 1900-01-15 | 1900-01-29 | 50%
| Resolve Bugs and Update Code | 1900-01-14 | 1900-01-04 | 1900-01-14 | 1900-01-02 | 5%
Deployment and Maintenance
| Deploy Website to Live Hosting Environment | 1900-01-14 | 1900-01-04 | 1900-01-14 | 1900-01-02 | 5%
| Monitor Website Performance Post-Launch | 1900-01-14 | 1900-01-04 | 1900-01-14 | 1900-01-02 | 5%
| Plan for Ongoing Updates and Maintenance | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
Project Management and Reporting
Milestone Reviews
| Milestone 1 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Milestone 2 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Milestone 3 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Milestone 4 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Milestone 5 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
Progress Presentations
| Presentation 1 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Presentation 2 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Presentation 3 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Presentation 4 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%
| Presentation 5 | 1900-01-14 01:36 | 1900-01-05 12:48 | 1900-01-14 01:36 | 1900-01-03 19:12 | 8%